## UAT
|  |  |  | Date | 2022-11-19
|  |  |  | Team ID | PNT2022TMID35886
|  |  |  | Project Name | Real-Time Communication System Powered by AI for Specially Abled
|  |  |  | Maximum Marks | 4 marks
Test case ID | Feature Type | Component | Test Scenario | Pre-Requisite | Steps To Execute | Test Data | Expected Result | Actual Result | Status | Executed By
Register_TC_OO1 | Functional | Register page | Verify whether the user is able to register his account when clicked on Register button |  | 1.Open the web app and click on Register button to register 2.Enter the required credentials and press submit | E-Mail : mohni@gmail.com Name: Mohnish Password: 1234 | The user details must be stored in database and the user must see success message | Working as expected | Pass | Mohnish S
Register_TC_OO2 | UI | Register page | Verify the UI elements in Signup page |  | 1.Open the app and click on Register button to register 2.Verify Singup page with below UI elements: a. Email text-box b. Name text-box c. Password text-box d. Register button e. Back to Home button | E-Mail : krish@gmail.com Name: Krishna Password: 1234 | Application should show below UI elements: a. Email text-box b. Name text-box c. Password text-box d. Register button e. Back to Home button | Working as expected | Pass | Krishna Kumar P
Register_TC_OO3 | Functional | Register page | Verify user cannot create a account using a invalid E-Mail Id |  | 1.Open the app and click on Register button to register 2.Enter sn invalid Mail ID and press register | E-Mail Id: ranjith | User should not be allowed to register for the new account | Working as expected | Pass | Ranjith V
Login_TC_OO1 | Functional | Login page | Verify user is able to log into application with valid credentials |  | 1.Open the app 2.Enter Valid email in Email text box 3.Enter valid password in password text box 4.Click on Login button | E-mail: beulah@gmail password: 1234 | User should be taken into the dashboard | Working as expected | Pass | Beulah Divya Kannan
Login_TC_OO2 | Functional | Login page | Verify user is unable to log into application with invalid credentials |  | 1.Open the app 2.Enter Valid email in Email text box 3.Enter valid password in password text box 4.Click on Login button | E-Mail : mohni@gmail.com Password: 12 | Application should show 'Username and Password Mismatch' message. | Working as expected | Pass | Mohnish S
Login_TC_OO3 | UI | Login page | Verify the UI elements in login page |  | 1.Open the app 2.Verify Login page with below UI elements: a.E-Mail Id text box b.password text box c.Login button | E-mail: beulah@gmail password: 1234 | Application should show below UI elements: a.E-Mail Id text box b.password text box c.Login button in green colour | Working as expected | Pass | Beulah Divya Kannan
dashboard_TC_OO1 | UI | Dashboard | Verify whether the user is able to view the greeting message with his/her name |  | Open the app and login |  | A Welcome message greeting the user with his/her name will be displayed | Working as expected | Pass | Krishna Kumar P
dashboard_TC_OO2 | UI | Dashboard | Verify the UI elements on the dashboard |  | 1. Open the app 2. Verify dashboard page with below UI elements: a. Welcome message b. Projrct description c. Convert Sign button in green color d. Logout button in red color |  | Application should show below UI elements: a. Welcome message b. Projrct description c. Convert Sign button in green color d. Logout button in red color | Working as expected | Pass | Ranjith V
dashboard_TC_OO3 | Functional | Dashboard | Verify whether the user is able to go to the Sign Converter page |  | 1.Open the app and login 2.Click on Convert Sign button |  | The user will be taken to the Sign Converter Page | Working as expected | Pass | Mohnish S
dashboard_TC_OO4 | Functional | Dashboard | Verify if the user is able to Logout |  | 1.Open the app and login 2.Click on Logout button |  | User should be logged out and taken to the Login page | Working as expected | Pass | Krishna Kumar P
sign_to_text_converter_page_TC_001 | UI | Sign to Text Converter page | Verify the UI elements on the Sign to Text converter page |  | 1. Open the app 2. Verify Sign to Text Converter page with below UI elements: a. Camera feed b. Homepage button c. Prediction text d. Translate sign button in green color |  | Application should show below UI elements: a. Camera feed b. Homepage button c. Prediction text d. Translate sign button in green color | Working as expected | Pass | Ranjith V
sign_to_text_converter_page_TC_002 | Functional | Sign to Text Converter page | Verify if the camera feed/input is working properly |  | Bring any object infront of device camera and see if it is captured on the app |  | The camera feed shows the object in front of the camera | Working as expected | Pass | Beulah Divya Kannan
sign_to_text_converter_page_TC_003 | Functional | Sign to Text Converter page | Verify if the user can go to the dashboard from this page |  | Click on the Homepage button |  | User is taken to the dashboard page | Working as expected | Pass | Krishna Kumar P
sign_to_text_converter_page_TC_004 | Functional | Sign to Text Converter page | Verify if the Translate Sign button actually translates the sign |  | 1. Show a sign in front of camera 2. Press the Translate Sign button |  | The Sign shown is converted into English Text | Working as expected | Pass | Ranjith V
sign_to_text_converter_page_TC_005 | Functional | Sign to Text Converter page | Verify if the translated sign is displayed as text on screen |  | 1. Show a sign in front of camera 2. Press the Translate Sign button | Sign for G | G | Working as expected | Pass | Mohnish S
sign_to_text_converter_page_TC_006 | Functional | Sign to Text Converter page | Verify if the text is converted into audible voice |  | 1. Show a sign in front of camera 2. Press the Translate Sign button | Sign for Space | Audio output saying Space | Working as expected | Pass | Mohnish S

## Testscearnios
S No. | Test Scenarios
1 | New user Registration using email, username and password
2 | Attempt to register using incorrect format or invalid email address
3 | Attempt to login using wrong email or password
4 | Logging in with correct credentials
5 | Dynamic generation of user name on Dashboard with welcome greeting
6 | Loading live input feed from camera into the web app
7 | Generation of converted/translated sign into text on screen
8 | Generation of audio output after translating sign into English text
9 | Logging an user out